## README
Calyx Containers — Flex Sourcing Program Tracker
Working companion to the Flexible Packaging Sourcing Program Playbook. Kickoff: Week of Mon Jun 29, 2026. North star: 50 factories.
Tab | What it's for
Roadmap | Wave/phase roadmap (Wave 1 → Wave 2 → Flexo/Roto → Tins → Pop-top tubes → Boxes), dated.
Weekly Timeline | Week-by-week goals for both tracks (Weeks 1-12), cumulative contracted, gates.
Supplier Pipeline Tracker | MASTER vendor list. One row per candidate. Pre-loaded with the Week-0 warm pipeline.
Sprint Scorecard | Per-sprint + cumulative KPIs. Auto-computed from the Pipeline Tracker (no manual tallying).
Contract & Document Status | Per-vendor contract paper status (NDA/MSA/annex), Calyx-legal-name check, IP/non-compete.
Risk Register | Program risks, likelihood/impact, mitigation, owner.
Reference Lists | Dropdown source values (Track, Tier, Stage, Category, etc.). Edit here to change dropdowns.
Key rule | A vendor is CONTRACTED when it has an MSA_Date AND Capability_Verified = "Y" (real manufacturer, not a broker). Trial / PSI / AQL run on the follow-on qualification track and do NOT block the contract gate.
Stages | Identify → Screen → Qualify → NDA → RFQ → Sample → Tour/Audit → Contracted → Qualifying → Active (or Parked).
Tiers | T1 = primary · T2 = backup · T3 = pipeline.
Legend | Status RAG: Green = on track · Amber = at risk · Red = blocked. Amber fill = sourcing gap / needs verification.

## Roadmap
Wave & Phase Roadmap
Flex first; later phases telescope. Identification leads contracting by one sprint; qualification trails it.
Wave / Phase | Scope | Domestic (Jake) | International (Steven +2) | Sprint / Weeks | Exit gate
Wave 1 — Digital flex (beachhead) | Domestic digital mid-web ("Spaceship") + intl digital flex; pair w/ labels | 2 → NDA+MSA+capability | 1 → NDA/MSA + factory tour | Sprint 1 / Wks 1-2 | 3 contracted; intl tour done; qual track opened; PackOS fields live
Wave 2 — Flex scale ("quick second") | More flexpack (digital + early flexo-capable) | +3 | +3 Guangdong (incl. >=1 Vietnam) | Sprint 2 / Wks 3-4 | Cum. 9; all tier-tagged; Wave 1 trials/PSI in motion
Phase 3 — Flexo / Rotogravure | High-volume flexo + roto, both tracks | +2-3 | +2-3 (Guangdong + East China) | Sprints 3-4 / Wks 5-8 | Cum. ~15; Wave 1 go/no-go; first T1 promotion; ~30% to 50
Phase 4 — Tin containers | Tins (mine CNY-list tin vendors) | +2 | +2-3 | Sprints 5-6 / Wks 9-12 | Cum. ~19-20; dual-country live >=1 category
Phase 5 — Pop-top tubes | Pre-labeled pop tubes (#1 new intl request) | support | +3 (pre-label capable) | Sprints 6-7 / Wks 11-14 | Pre-label pop-tube trial; label+tube spec in PackOS
Phase 6 — Boxes (Rigid/CR + SBS/Display) | Rigid/CR + SBS/display | +2 | +2-3 (East China + Vietnam paper offset) | Sprints 7-9 / Wks 13-18 | Cum. ~28-30+; Phase 2 Scale ($500K->$2M) underway

## Weekly Timeline
Weekly Goal Timeline (Weeks 0-12)
Kickoff Mon Jun 29, 2026. Holidays: Fri Jul 3 (sign by Thu Jul 2); Mon Sep 7 Labor Day (move sync to Tue Sep 8).
Wk | Dates | Domestic (Jake) | International (Steven +2) | Cum. contracted | Gate / milestone
0 | Jun 22-26 | Build warm pipeline; templates/signature/Legal SLA; open PackOS fields; deposit envelope | Same — warm Guangdong list + CNY-vendor outreach | 0 | Pre-work complete
1 | Jun 29-Jul 3 | Down-select 2 digital mid-web; RFIs/NDAs out; samples requested | NDA out; factory tour executed; MSA issued | 0 | Sprint 1 midpoint
2 | Jul 6-10 | 2 domestic NDA+MSA + capability verified | 1 intl NDA/MSA + tour + capability verified | 3 | * Wave 1 contracted; first Supply Web entries
3 | Jul 13-17 | Down-select 3 dom flexpack; RFQs out | 3 Guangdong (incl. >=1 Vietnam) NDAs/tours scheduled | 3 | Sprint 2 start; Wave 1 trials in transit
4 | Jul 20-24 | +3 domestic contracted | +3 intl contracted + tours | 9 | * Wave 2 contracted (+3/+3); roto sourcing begins
5 | Jul 27-31 | Identify dom flexo/roto; Wave-1 samples approved | Flexo/roto NDAs; tours; Wave-1 samples arrive | 9 | Sprint 3 start
6 | Aug 3-7 | +1-2 dom flexo; Wave-1 dom -> T1 | +1-2 intl flexo; tours done | ~12 | Wave 1 intl PSI result in
7 | Aug 10-14 | Roto contracting; manage trials | +1 intl roto; Wave-1 first shipment clears (ISF 10+2) | ~13 | * Wave 1 intl go/no-go
8 | Aug 17-21 | +2-3 dom flexo/roto total | +2-3 intl flexo/roto total | ~15 | * Phase 3 contracted; Month-2 checkpoint; ~30% to 50
9 | Aug 24-28 | Identify dom tin | Intl tin NDAs (CNY-list); Vietnam activated | ~15 | Dual-country live
10 | Aug 31-Sep 4 | +2 dom tin | +2 intl tin; tours | ~19 | Nearing Yr-1 "20 certified"
11 | Sep 7-11 | Tin qualified; pop-tube support | Pre-label pop-tube NDAs/tours; +1 MSA | ~20-21 | * 20-factory milestone (~40% of 50)
12 | Sep 14-18 | Identify dom boxes | +2 intl pop-tube; box sourcing begins | ~22-23 | * End-of-POC (Month 3) go/no-go; ~45% to 50

## Supplier Pipeline Tracker
Supplier Pipeline Tracker (master)
One row per candidate vendor. CONTRACTED = MSA_Date filled AND Capability_Verified = "Y". Pre-loaded with the Week-0 warm pipeline.
| Vendor_ID | Digital /Flexo / Roto | Vendor_Name | Status | Website | Track | Country | Cluster | Category | Sub_Capability | Tier | Primary/Secondary | Stage | Owner | Wave Sprint | NDA Date | MSA Date | Capability Verified | Factory Tour Date | RFQ Sent | Quote Received | Quoted Price | Target Price | Price vs Target % | MOQ | Deposit % | Lead_Time_Days | AQL_Standard | PSI_Status | Trial_Order_No | Trial_Result | Command_Integrated | PackOS_Handoff | IP_Clause | NonCompete_24mo | Status_RAG | Next_Action | Next_Action_Due
1 | FLEX-D-001 | Flexographic | DazPak Flexible Packaging | Active |  | Domestic | USA | US-CA | Domestic Flexographic | Pouches/rollstock, low MOQ | T1 | Primary | Qualify | Jake King | S1
1 | FLEX-D-002 | Digital | Ross Print & Packaging | Active |  | Domestic | USA | US-WA | Domestic Digital | HP Indigo + flexo + labels | T2 | Secondary | Qualify | Jake King | S1
1 | FLEX-D-004 | Flexographic | Morris Packaging | Active |  | Domestic | USA | US-IL | Domestic Flexographic | Pouches/roll stock, sustainable films | T2 | Secondary | Identify | Jake King | S2
1 | FLEX-D-005 | Digital | InkWorks Printing | Active |  | Domestic | USA | US-WI | Domestic Digital | PS labels, pouch/mailer print | T3 | Secondary | Identify | Jake King | S2
1 | FLEX-D-007 | Rotogravure | Takigawa Corp. America | Active |  | Domestic | USA | US-KY | Domestic Rotogravure | High-barrier pouches/rollstock | T1 | Primary | Identify | Jake King | S3
1 | FLEX-I-002 | Rotogravure | TedPack Company Ltd. | Active |  | International | China | Guangdong | International Rotogravure | Custom pouches; ISO/BRCGS/BSCI | T1 | Primary | Identify | Steven Yao | S2
1 | FLEX-D-003 | Digital | Lauterbach Group | Not Contacted | https://www.lauterbachgroup.com/ | Domestic | USA | US-WI | Domestic Digital
1 | FLEX-D-006 | Digital | Brand my Bags | In Process | https://brandmybags.com/ | Domestic | USA | US-WI | Domestic Digital |  |  |  |  | Jake King | S1 | 2026-06-24
1 | FLEX-D-008 | Digital | Impackt | In Process |  | Domestic | USA | US-CA | Domestic Digital |  |  |  |  | Jake King | S1
1 | FLEX-D-009 | Digital | The Pouch House | Not Contacted | https://www.thepouchhouse.com/ | Domestic | USA | US-MN | Domestic Digital
1 | FLEX-I-001 | Rotogravure | Dongguan Xueliang Packaging | Not Contacted | http://dgbpack.com/Cases.html | International | China | Guangdong | International Digital | CR Pouch — verify digital print | T3 | Secondary | Identify | Steven Yao | S1
1 | FLEX-I-003 | Digital / Rotogravure | BowePack (Guangdong Bowe Packaging) | Not Contacted | https://bowepack.com/ | International | China | Yunfu City, Guangdong
1 | FLEX-I-004 | Rotogravure | Wellfapack (Shantou Wellfa) | Not Contacted | https://wellfapack.com/about-shantou-wellfa-print-pack-co-ltd/ | International | China | Shantou, Guangdong
1 | FLEX-I-005 | Digital / Rotogravure | Gozen Packaging | Not Contacted | https://www.gozenpackaging.com/pcr-packaging-bags/ | International | China
1 | FLEX-I-006 | Rotogravure | Qiyu Pack | Not Contacted | https://qiyupack.com/ | International | China
1 | FLEX-I-007 | Rotogravure | Saigon Trapaco | Not Contacted | https://saigontrapaco.com.vn/vi/index.html | International | Vietnam | Ho Chi Minh City area
1 | FLEX-I-008 | Rotogravure | Ngai Mee Packaging Vietnam | Not Contacted | https://ngaimee.com/ | International | Vietnam
1 | FLEX-I-009 | Rotogravure | Amiba | Not Contacted | https://amibapack.com/en/product/tui-dung-2/ | International | Vietnam
1 | FLEX-I-010 | Rotogravure | SIVICO JSC | Not Contacted | https://www.sivico.com.vn/en/contact.html | International | Vietnam | Hai Phong
1 | FLEX-I-011 | Digital | ASUWANT PACKAGING | In Process | https://www.asuwantpackaging.com/ | International | China | Jiang Men | International Digital | International Rotogravure + Paper Box
2 | TUBE-I-001 |  | Yiwu Sucheng Packaging | Not Contacted |  | International | China | East China | Pop-top Tubes | Pop Top Tube | T2 | Primary | Identify | Steven Yao | S6
2 | TUBE-I-002 |  | Mitsuiwa Shinko (MTS) | Not Contacted |  | International | Taiwan | Taiwan | Pop-top Tubes | Paper tube, paper box | T3 | Secondary | Identify | Steven Yao | S6
2 | TUBE-I-003 | Maybe Broker? | ZAAM INTERNATIONAL CO., LTD | Not Contacted |  | International | Vietnam
2 | TUBE-I-004 |  | JK Packaging | Not Contacted | https://jk-packaging.com/ | International | China
2 | TUBE-I-005 |  | Dewei Plastics | Not Contacted | https://www.dwplastic.com/ | International | China
3 | TIN-I-001 |  | TinWonder (Dongguan) | Early Conversations |  | International | China | Guangdong | Tins | Tinplate boxes & cans, 2,000+ molds | T1 | Primary | Identify | Steven Yao | S5
3 | TIN-I-002 |  | Andylots Tin Box | Early Conversations |  | International | China | Guangdong | Tins | CR tins for cannabis | T1 | Primary | Identify | Steven Yao | S5
3 | TIN-I-003 |  | Dongguan Lianglvfang | Not Contacted |  | International | China | Guangdong | Tins | Tin CR/Non-CR, Slide Tin CR | T2 | Secondary | Identify | Steven Yao | S5
3 | TIN-I-004 |  | Dongguan Xinyu Tin Can | Not Contacted |  | International | China | Guangdong | Tins | Tin | T3 | Secondary | Identify | Steven Yao | S5
3 | TIN-I-005 |  | Foshan Yuelida Metal Cap | Not Contacted |  | International | China | Guangdong | Tins | Tin | T3 | Secondary | Identify | Steven Yao | S6
3 | TIN-I-006 |  | Paulin Vina | Not Contacted |  | International | Vietnam | Vietnam | Tins | Tin (Vietnam tariff hedge) | T2 | Secondary | Identify | Steven Yao | S6
4 | BOX-D-001 |  | California Packaging & Display | Different Scope/ Not Contacted |  | Domestic | USA | US-CA | Boxes (SBS/Display) | Folding cartons, POP displays | T1 | Primary | Identify | Jake King | S7
4 | BOX-D-002 |  | Virtual Packaging | Active |  | Domestic | USA | US-TX | Boxes (Rigid/CR) | Rigid boxes, CR, prototyping | T2 | Secondary | Identify | Jake King | S7
4 | BOX-I-001 |  | Dongguan Fuyang Printing | Not Contacted |  | International | China | Guangdong | Boxes (Rigid/CR) | Paper/CR/Rigid/Magnetic box | T2 | Primary | Identify | Steven Yao | S7
4 | BOX-I-002 |  | TaPuMei Printing | Not Contacted |  | International | China | Guangdong | Boxes (Rigid/CR) | CR/Set-up/Flat/Magnetic box | T2 | Secondary | Identify | Steven Yao | S7
4 | BOX-I-003 |  | Intramedia Dongguan | Not Contacted |  | International | China | Guangdong | Boxes (Rigid/CR) | CR/Flat/Setup box | T3 | Secondary | Identify | Steven Yao | S7
4 | BOX-I-004 |  | Intramedia Minh Duc | Not Contacted |  | International | Vietnam | Vietnam | Boxes (SBS/Display) | Paper box (Vietnam) | T3 | Secondary | Identify | Steven Yao | S7
4 | BOX-I-005 |  | Putian Jusheng Packing | Not Contacted |  | International | China | Fujian | Boxes (SBS/Display) | Paper box, shopping bag | T3 | Secondary | Identify | Steven Yao | S8
4 | BOX-I-006 |  | Zhongshan Daqian Display | Not Contacted |  | International | China | Guangdong | Boxes (SBS/Display) | Pedestal display | T3 | Secondary | Identify | Steven Yao | S8
| LBL-I-001 |  | Ningbo Brothers Printing | Not Contacted |  | International | China | East China | Labels | Label printing (beachhead pair) | T3 | Secondary | Identify | Steven Yao | S2

## Sprint Scorecard
Sprint Scorecard
Auto-computed from the Supplier Pipeline Tracker. Wave_Sprint values (S1..S9) drive the per-sprint counts. Target = 50 factories.
Sprint | Weeks | Dates | Target_Contracted | Actual_Contracted | NDAs_Executed | MSAs_Executed | Tours_Completed | Capability_Verified | Trial_Orders_Placed | Cumulative_Contracted | %_to_Target_50 | RAG | Commentary
S1 | Wks 1-2 | Jun 29 - Jul 10 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0% | Green
S2 | Wks 3-4 | Jul 13 - Jul 24 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Green
S3 | Wks 5-6 | Jul 27 - Aug 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Green
S4 | Wks 7-8 | Aug 10 - Aug 21 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Green
S5 | Wks 9-10 | Aug 24 - Sep 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Green
S6 | Wks 11-12 | Sep 7 - Sep 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Green
TOTAL (to date) |  |  | 22 | 0 | [5 empty] | 0 | 0%

## Contract & Document Status
Contract & Document Status
One row per contract document. ALL international docs must be in Calyx Containers' legal name.
Vendor_ID | Vendor_Name | Doc_Type | Calyx_Legal_Entity_Named | Sent_Date | Signed_Date | Countersigned | IP_Clause | Defect_Penalty_Clause | NonCompete_24mo | Milestone_Payment_Terms | ROFR_Steven_Staff | Status | Notes

## Risk Register
Risk Register
Review at every bi-weekly sprint sync. Escalate per the SLT 24-hour rule.
# | Risk | Likelihood | Impact | Mitigation | Owner | Trigger / Early signal | Status
1 | 2-week contracting erodes diligence | M-H | H | Contracted != qualified; MSA carries trial+PSI exit ramp; cap full-run spend until AQL pass | Cory | Trial/PSI fails after signing | Open
2 | Legal countersignature throughput (6 in Wks 3-4) | M-H | H | Pre-approve 2 master templates (Wk 0); 48-hr Legal SLA; redline-only; off-template -> 24-hr escalation | Legal / A: Cory | Any MSA waiting >48h | Open
3 | Intl qualification lag (PSI/customs can't fit in-sprint) | H | M-H | Gate = contracted + tour + capability; go/no-go Wks 6-8; never promise qualified intl in 2 wks | Steven / A: Cory | PSI slips past Wk 8 | Open
4 | Warm-pipeline depletion after Wave 2 | M-H | H | Identification runs a sprint ahead; continuously feed pipeline | Cory | <5 named candidates per open slot | Open
5 | Section 301 tariffs raise China landed cost | H | H | China+Vietnam dual-country Day 1; >=1 Vietnam by Wave 2; model landed cost both origins | Steven / A: Cory | Tariff action announced | Open
6 | Key-person dependency on Steven | M | H | All docs in Calyx name; IP clause; 24-mo non-compete; ROFR on 3 staff; Cory holds docs + relationship map | Cory | Steven availability change | Open
7 | MOQ / deposit cash exposure | M | H | Milestone/phase-gate payments; trials first; per-sprint deposit cap; breach -> escalate to Heath | Cory / A: Heath | Deposit request > cap | Open
8 | Quality / prepress failure (flex digital art) | M | H | Mandatory 3rd-party PSI at AQL; trials before full runs; defect penalty in every MSA | Quality / A: Cory | Trial defect rate > AQL | Open
9 | Guangdong supplier concentration | M | M | Treat Guangdong-only categories as single-source; require T2 outside Guangdong/in Vietnam | Cory | Category with only Guangdong T1 | Open
10 | PackOS / Command integration gaps | M | M-H | Define handoff fields at Wave 1; vendor not 'done' until data lands; interim sheet + backfill | Cory | Data not landing in PackOS | Open
11 | CNY blackout (~3 wks Jan/Feb, annual) | H | M-H | Bake into lead-time KPI; pre-CNY buffer builds; non-issue for mid-2026 start, recurring after | Steven / A: Cory | Approaching Jan | Open

## Reference Lists
Reference Lists
Dropdown source values — edit a column to change the dropdowns used across the tracker.
Track | Tier | Primary/Secondary | Stage | Category | Capability Verified | PSI Status | RAG | Yes/No
Domestic | T1 | Primary | Identify | Domestic Digital | Y | Not started | Green | Y
International | T2 | Secondary | Screen | Domestic Flexographic | N | Booked | Amber | N
| T3 |  | Qualify | Domestic Rotogravure | Pending | Passed | Red
|  |  | NDA | International Digital |  | Failed
|  |  | RFQ | International Rotogravure |  | N/A
|  |  | Sample | Labels
|  |  | Tour/Audit | Shrinks
|  |  | Contracted | Flex Materials
|  |  | Qualifying | Tins
|  |  | Active | Pop-top Tubes
|  |  | Parked | Boxes (Rigid/CR)
Boxes (SBS/Display)